## Sheet1
"Semester Project" - Gantt Chart
Task | Start | End | Duration | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
|  |  |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
REQUIREMENTS | 17.08.20 | 23.08.20 | bar: Week 1 17 to Week 1 23
*Project plan
*Pencil sketches of the site
DESIGN | 24.08.20 | 30.08.20 | bar: Week 2 24 to Week 2 30
*Drawings
*Color&Graphics
*Fonts (colors, sizes)
*Content writing and assembly
CONSTRUCTION | 31.08.20 | 06.09.20 | bar: Week 3 31 to Week 3 6
*HTML/CSS development for mobile devices
*CSS development for laptop/desktop devices
*Testing
IMPLEMENTATION | 07.09.20 | 13.09.20 | bar: Week 4 7 to Week 4 13